## Sheet1
Stage | BDM | Branch | Project Name | Event Name | Venue | Area (Sqm) | Event Start Date | Event End Date | Material Dispatch Date | Installation Start Date | Installation End Date | Dismantling Date | Project Manager | Team Type | Senior Carpenter | Display Service Team | Company Electrician | O/S Electrician
Brief | Shivani | Vasai | Wipro | The Leela Palace | Chennai | 36 | 20th March 2026 |  | 17th March 2026 | 19th March 2026 |  | 20th March 2026 | Abhijit | Shamshad
Confirmed | Vinodji | Manesar | ZF | Factory Set up | Coimbatore | 109 | 23rd March 2026 |  | 18th March 2026 | 21st March 2026 | 22nd March 2026 | NA | Ajit | Insta | Rajkumar + 3 o/s |  |  | O/s Suvash - 1 person
Brief | DG Sir | Manesar | Havells | Acereflect 2026 | Goa | 60 | 27th March 2026 | 28th March 2026 | 22nd March 2026 | 25th March 2026 | 26th March 2026 | 28th March 2026 | Uday | Insta | Ramashish + Sharda 3 | Jitesh + Vivek |  | O/s Suvash - 2 person
Design | DG Sir | Vasai | De Décor | Internal Event | Mumbai |  | 4th April 2026 | 5th April 2026 | 2nd April 2026 | 3rd April 2026 |  | 5th April 2026 |  | Insta
Confirmed | Shivani | Vasai | Wipro | Taj west End | Bnagalore | 36 | 10th April 2026 |  |  | 9th April 2026 |  |  | Abhijit | Shamshad
Brief | DG Sir | Vasai | Reliance | Fab expo | JIO Mumbai | 225 | 16th April 2026 | 18th April 2026 | 12th April 2026 | 13th April 2026 | 15th April 2026 | 18th April 2026 | Uday, Pradeep | Shamshad
Design | Shivam | Vasai | Zoloto | Plumbex 2026 | Bangalore | 54 | 16th April 2026 | 18th April 2026 | 10th April 2026 | 13th April 2026 | 15th April 2026 | 18th April 2026 | Abhijit, Prakash | Shamshad
Design | Shivam | Vasai | Faunc India | Tagma | Mumbai | 308 | 21st April 2026 | 24th April 2026 | 16th April 2026 | 17th April 2026 | 20th April 2026 | 24th April 2026 |  | Shamshad
Design | Shivam | Vasai | Proterial | Tagma | Mumbai | 240 | 21st April 2026 | 24th April 2026 | 16th April 2026 | 17th April 2026 | 20th April 2026 | 24th April 2026 |  | Insta
Confirmed | Sourjit | Manesar | Agilent | Analytica | JIO Mumbai | 72 | 22nd April 2026 | 24th April 2026 | 18th April 2026 | 19th April 2026 | 21st April 2026 | 24th April 2026 | Satyendra | Insta
Confirmed | Sourjit | Manesar | Analitika Jena | Analytica | JIO Mumbai | 30 | 22nd April 2026 | 24th April 2026 | 18th April 2026 | 19th April 2026 | 21st April 2026 | 24th April 2026 | Ajit | Insta
Confirmed | Rajveer | Manesar | IHM Valves | India Pharma | Hyderabad | 35 | 23rd April 2026 | 25th April 2026 | 18th April 2026 | 20th April 2026 | 22nd April 2026 | 25th April 2026 |  | Insta
Design | DG Sir | Vasai | Havells | Smart Home Expo | JWC BKc | 105 | 28th April 2026 | 30th April 2026 | 25th April 2026 | 26th April 2026 | 27th April 2026 | 30th April 2026 | Satyendra | Shamshad
Design | Vinodji | Vasai | PRO FX | Smart Home Expo | JWC BKc | 154 | 28th April 2026 | 30th April 2026 | 25th April 2026 | 26th April 2026 | 27th April 2026 | 30th April 2026 |  | Shamshad
Design | Rajveer | Vasai | Aditya Chemical | Chemexpo 2026 | Mumbai | 18 | 29th April 2026 | 30th April 2026 | 26th April 2026 | 26th April 2026 | 28th April 2026 | 30th April 2026 | Abhijit | Shamshad
Negotiation | DG Sir | Vasai | Havells | Ace Reflect 2026 | Indore | 60 | 2nd May 2026 | 3rd May 2026 |  |  |  |  | Uday | Shamshad
Negotiation | Shivani | Vasai | Wipro | Marriot | Kolkata | 36 | 8th May 2026 | [6 empty] | Shamshad
Negotiation | Shivani | Vasai | Wipro | The West In | Pune | 36 | 22nd May 2026 | [6 empty] | Insta
Negotiation | DG Sir | Vasai | Havells | Ace Reflect 2026 | Chennai | 60 | 23rd May 2026 | 24th May 2026 | [5 empty] | Insta
Design | DG Sir | Vasai | Havells | Ace Reflect 2026 | Raipur | 60 | 20th June 2026 | 21st June 2026 | [5 empty] | Insta
Design | Shivani | Vasai | Wipro | Avadh Utopia | Surat | 36 | 5th June 2026 | [6 empty] | Insta
Design | DG Sir | Vasai | Havells | Ace Reflect 2026 | Jaipur | 60 | 18th Jul 2026 | 19th Jul 2026 | [5 empty] | Insta
Design | Shivani | Vasai | Wipro | Jade Banquet | Ahmedabad | 36 | 19th June 2026 | [6 empty] | Insta
Design | Shivani | Vasai | Wipro | Grand Sherton | Indore | 36 | 3rd July 2026 | [6 empty] | Insta
Confirmed | Shivani | Manesar | Wipro | Sayaji | Raipur | 36 | 17th July 2026 | [6 empty] | Insta
Confirmed | Shivani | Manesar | Wipro | Hyatt Regency | Chandigrah | 36 | 31st July 2026 | [6 empty] | Insta
Design | DG Sir | Manesar | Havells | Ace Reflect 2026 | Coimbatore | 60 | 8th Aug 2026 | 9th Aug 2026 | [5 empty] | Insta
Design | Shivani | Manesar | Wipro | Marriot | Jaipur | 36 | 13th Aug 2026 | [6 empty] | Insta